## Risk_Tracking_Template
Risk Register
Date of last review:
ID | Description of Risk | Impact | Risk Reponse | Risk Level | Risk owner | Notes
1 | Website downtime or server crashes. | Loss of sales; dissatisfied customers; damage to reputation | Set up server monitoring and backups; implement 24/7 tech support; use Content Delivery Networks (CDNs) | High | Yahia | Use cloud hosting; ensure maintenance downtime is scheduled and communicated to customers
2 | Payment gateway failures (e.g., credit card processing) | Transactions fail; loss of revenue; customer frustration | Regularly test payment gateways; integrate multiple payment options (PayPal, Stripe, etc.) | High | Nouran | Implement fraud protection to ensure security and trust with customers
3 | Customer data exposure; loss of trust; legal implications | Customer data exposure; loss of trust; legal implications | Implement SSL encryption; regular security audits; compliance with PCI DSS standards | High | Malak | Train staff on phishing scams and data protection
4 | Poor website UX/UI causing cart abandonment | High bounce rates; loss of orders; negative user experience | Regular UX testing; improve website flow; make checkout process as simple as possible | Medium | Yahia | Collect customer feedback to improve user interface regularly
5 | Incorrect menu or product listing information (pricing, availability) | Customer dissatisfaction; order cancellations; reputation damage | Implement real-time inventory updates; ensure accurate menu pricing | Medium | Nouran | Provide customers with “out of stock” alerts or availability status updates
6 | Delayed order processing or dispatching | Late deliveries; customer complaints; potential refunds or cancellations | Improve order fulfillment systems; partner with reliable delivery services; automate order confirmation | High | Malak | Track orders in real-time; notify customers of delays
7 | Lack of mobile optimization (not user-friendly on mobile devices) | Loss of customers; reduced conversions | Ensure website is mobile-friendly; implement responsive design | Medium | Yahia | Prioritize mobile shopping experience given the demand for convenience on smartphones
8 | Inadequate customer support (slow response, unhelpful) | Negative customer experience; loss of repeat business | Set up live chat, chatbot, and fast email response systems; hire dedicated support agents | Medium | Nouran | Monitor response times and train staff on conflict resolution
9 | Negative online reviews (on social media or review sites) | Damage to brand reputation; loss of customer trust | Monitor reviews daily; engage with customers on feedback (positive or negative) | Medium | Malak | Implement a strategy for responding to negative reviews with empathy and solutions
10 | Inaccurate delivery address or customer contact info | Delays in delivery; customer complaints | Implement address validation tools; confirm customer details during order placement | Medium | Yahia | Send confirmation emails or SMS with order and address details to verify
11 | Delivery drivers arriving late or missing deliveries | Negative customer experience; potential refunds or reschedules | Implement real-time GPS tracking; hire additional drivers during peak times | High | Nouran | Partner with reliable delivery services or use fleet management software
12 | Incorrect or missing items in delivery | Customer complaints; refunds; product loss | Implement double-checking at packing stage; use delivery tracking with item confirmation | High | Malak | Create clear guidelines for packing and labeling orders
13 | Incorrect COD payment handling (underpayment or no cash) | Loss of revenue; delivery returns; customer complaints | Confirm COD amount with customers during order placement; provide clear instructions on payment expectations | Medium | Nouran | Offer prepayment discounts to encourage credit card payments
14 | Environmental factors (e.g., heavy rain, traffic accidents) | Delivery delays; potential customer frustration | Use real-time traffic monitoring; communicate delays early to customers; have backup routes | Medium | Yahia | Provide weather-related updates to customers proactively
15 | Positive word-of-mouth or viral marketing (through social media) | Increased brand awareness; more customers | Encourage customers to share their experiences on social media; incentivize reviews with discounts | Medium | Nouran | Run referral or reward programs for users who spread the word
16 | Partnerships with local influencers or food bloggers | Increased sales and traffic; higher brand credibility | Collaborate with influencers to promote your offerings; create exclusive menu items for them | High | Yahia | Leverage influencers for limited-time offers or events
17 | New customer segments (e.g., corporate catering, family events) | Expanded market base; increased sales | Offer catering options for businesses or large family orders; market to corporate clients | Medium | Yahia | Build partnerships with local businesses for consistent orders
18 | Special promotions during holidays (e.g., Ramadan, Eid) | Increased sales volume; customer engagement | Plan and promote seasonal discounts or meal bundles during holidays | High | Malak | Create holiday-specific content and promotions to capitalize on festive seasons
19 | Improving loyalty program or subscription service | Higher customer retention; increased repeat orders | Implement a rewards program or subscription box to encourage regular customers | Medium | Malak | Offer discounts or exclusive access to loyal customers to enhance engagement
20 | Food quality deterioration during transport | Customer dissatisfaction; potential food safety issues | Use temperature-controlled packaging; ensure quick delivery routes | High | Nouran | Regularly test delivery times and quality for feedback
21 | High demand during peak hours (e.g., lunch, dinner times) | Delays in delivery; overwhelmed staff; customer dissatisfaction | Prepare in advance for peak times; use forecasting tools to predict demand | High | Malak | Implement order limits or take pre-orders to avoid overloading
22 | Food delivery items getting damaged in transit | Poor customer experience; refund requests; loss of product | Use sturdy packaging; clearly label fragile items; train drivers on careful handling |  | Malak | Optimize packaging for heat preservation and item protection
23 | Order mistakes due to miscommunication between kitchen and delivery team | Incorrect or missing orders; customer dissatisfaction | Implement a clear communication system between kitchen and delivery staff | Medium | Yahia | Use tablets or apps for seamless communication between the kitchen and drivers
24 | Stock shortages for specific items | Lost sales; customer frustration; reduced order fulfillment | Set up real-time inventory management; notify customers of item unavailability promptly | Medium | Nouran | Offer substitutes or allow customers to adjust orders based on availability